## Project tracker
Project tracker |  |  |  | Percent over/under to highlighted numbers | 25%
Project | Category | Assigned to | Estimated start | Estimated finish | Estimated work (in hours) | Estimated duration (in days) | Actual start | Actual finish | Actual work (in hours) | Actual duration (in days) | Notes
Project 1 | Category 1 | Employee 1 | 2023-12-02 | 2024-01-31 | 210 | 59 | 2023-12-02 | 2024-02-05 | 300 | 63
Project 2 | Category 2 | Employee 4 | 2023-12-26 | 2024-01-26 | 400 | 30 | 2023-12-26 | 2024-01-29 | 390 | 33
Project 3 | Category 1 | Employee 2 | 2023-10-28 | 2023-12-27 | 500 | 59 | 2023-10-28 | 2024-01-09 | 500 | 71
Project 4 | Category 2 | Employee 3 | 2023-11-07 | 2023-11-17 | 250 | 10 | 2023-11-07 | 2023-11-26 | 276 | 19
Project 5 | Category 3 | Employee 2 | 2023-11-07 | 2023-12-17 | 300 | 40 | 2023-11-07 | 2023-12-23 | 310 | 46
Project 6 | Category 4 | Employee 4 | 2023-12-07 | 2023-12-17 | 500 | 10 | 2023-12-07 | 2023-12-22 | 510 | 15
Project 7 | Category 5 | Employee 1 | 2023-12-23 | 2024-01-16 | 750 | 23 | 2023-12-23 | 2024-01-21 | 790 | 28
Project 8 | Category 2 | Employee 1 | 2023-12-28 | 2024-02-05 | 450 | 37 | 2023-12-22 | 2024-01-31 | 430 | 39
Project 9 | Category 4 | Employee 1 | 2023-11-02 | 2023-11-22 | 250 | 20 | 2023-11-07 | 2023-11-17 | 200 | 10
SETUP

## Setup
Setup
Category Name | Employee Name
Category 1 | Employee 1
Category 2 | Employee 2
Category 3 | Employee 3
Category 4 | Employee 4
Category 5 | Employee 5
Category 6 | Employee 6
PROJECTS